## Sheet1
w | Solutions | Process challenges | Solution
Input data was shared in a different format/structure across WHS (~45 different formats). | Created a standard Structure for Input to our conversion codes. Created a code to handle the conversion of each file based on the WHS. Maintained a mapping by WHS to identify mandatory columns, pre-checks, harmonize colums and content across WHS and conversion to standard input. | Changing formats within a WHS between waves | informed the WHS after initial pre-checks revealed issues in the Datafile.
Received data in Microsoft Access Database (.accdb extension) which was not supported nin DataBricks system | Pre-converted the file to CSV using Python. | The Logics for each process (Datafile Conversion, Volume Conversion, Product/POS Matching, Competition data handling, etc.) were all very vague. The logics changed frequently | All the logics were documented (every time it changed) and signed-off by PMI before being applied to the conversion pipeline
Received data as a Pivot table where specific filters needed to be used as input | handles the data extraction from Pivot tables using Python | Mappings already being used for the Delivery (by a third party) was not shared with KANTAR. | Existing mapping had to be re-created manually using available information and sample Reports.
The Volume Conversion logic used for the same product varied between Markets and were sometimes WHS Specific | Created a mapping to document all the Volume Conversion logics across WHS to be used as input to the datafile conversion code. | No. of WHS/Accounts initially expected based on requirements - 20 No. of WHS/Accounts in the pipeline - 37
Overlapping time periods and data shared in different waves. | Picked up the data for the overlapping time period from the latest datafile (based on their wave) and ignored the older data. Data Restataement. | Delay in the files shared.
PMI Volumes were added as an Input mid-development. The data was pre-processed and did not fit into the existing conversion flow. | A new code was developed specifically to handle PMI Direct Volumes | Additional Output requirements : Accounts output, Pricing and PMI Direct (Weekly and Monthly)
Product and POS Mapping : Limited metadata available for mapping. In Most cases, only the Product/POS label was available for the identification with no other info. |  | PMI request to pre-pone the deliveries by over a month.
Mapping challenge 1 : Names used were different across markets with no defined structure or naming convention Mapping challenge 2 : A 'Match' involved : 1. Matching against PMI Database to identify PMI Products 2. Matching against PMI Volume of sales to WHS 3. Matching againt an existing codebook updated after every processing. 4. Matching criteria was not defined clearly and expectation was to do the mapping manually (search for details manually) | A fuzzy match logic was developed which assigns a 'Score' to the match. All other challenges were also handled with Python automation | Input Data Manipulation (Whs-SubWHS volume manipulation, Delhaize WHS specific data corrections,etc.) were added to the scope